## Slide 1
MAPLE MALL
Phone accessories
pop-up proposal
June 1–August 31, 2027
Customer evidence, financial target and first-month plan
Robin Lecomte, Caroline Kilbane, Nicolas Delfau, Jasmine Ongole
Notes: Committed team source: upstream/main 4ec519e88d9afe811a9d447f7aef8b3d81d473ce. Roles 01–03. User previously selected phone accessories. The committed Customer Analyst recommends packaged snacks at $3. This presentation preserves that conflict rather than describing the phone proposal as a unanimous team choice. Suggested duration: five minutes.

## Slide 2
Case overview
The opportunity
Maple Mall is 70% empty. Unit 42 offers 400 square feet beside the central court.
The proposed business
A phone accessories pop-up selling cases, cables and grips at an initial $18 per item.
The resources and timeline
$20,000 available, with no borrowing. Operate June 1–August 31, 2027. Rent is $2,500/month.
The decision to prove
Break even by month three while funding every expense. Base target: 1,926 sales, about 21/day.
Key constraints: trade 10 AM–9 PM daily. August passing traffic is expected to decline 30%.
2
Notes: Sources: inputs/mall_facts.md (70 empty units of 100, 400-square-foot Unit 42, $20,000 available, no borrowing, June 1–August 31 2027 lease, rent $2,500/month, mandatory 10 AM–9 PM daily trading, 30% expected August corridor-traffic decline); roles/01_customer_analyst/customers.md on upstream/main 707b044 (evaluate phone cases, cables and grips at $18); roles/02_finance_analyst/finance.md and daily_projection.csv (1,926 sales at the $18 full-price assumption, approximately 21/day). The financial target is a required-sales projection, not verified demand. It excludes the proposed 20% referral coupon, giveaways and outdoor poster costs on slide 7; the campaign requires a revised forecast.

## Slide 3
Customer evidence for phone accessories
2
Chart: 
| Snacks | Accessories | Craft bundles | Used books
Respondents | 60 | 25 | 10 | 5
Phone accessory interest
25% chose accessories. Price limits ranged from $18 to $25, averaging $20.60.
Customer recommendation
Evaluate $18 accessories across age groups. No accessory specialist is listed, but other sellers may carry them.
Saturday-only survey. Stated interest does not establish weekday demand or actual purchases.
Notes: Source: roles/01_customer_analyst/customers.md on upstream/main at 707b0449bca462fd71f7fb3fc3b603f5b7ee7c03. The working file in the finance branch is still the starter template; this slide uses the completed committed team report. 25 of 100 Saturday respondents select accessories. There are five accessory respondents in each of five age groups. Stated maximum prices run $18–$25, averaging $20.60 ($515/25). These are price limits, not transactions or product/model-specific demand. No directory business explicitly specializes in accessories, but general retailers and off-site sellers may carry them. Students are one potential audience, with actual demand unverified. Recommendation: evaluate cases, cables and grips at an initial $18 assumption and test compatibility demand. Original sources: inputs/shopper_survey.csv, inputs/competitors.csv, inputs/mall_facts.md, inputs/cost_list.md and inputs/foot_traffic.csv. Do not equate survey interest with the model's required 2.96% buying conversion.

## Slide 4
Three-month cost and cash requirements
3
Project expense | June–August
Staffing, all opening hours | $16,192.00
Rent | $7,500.00
Stock purchased, 1,950 items | $7,800.00
Card processing | $1,040.04
One-time setup and promotion | $1,450.00
Terminal, insurance, cleaning | $675.00
Total costs | $34,657.04
$7,650
Before opening, including the $2,500 deposit and June rent.
$7,875
Through opening-day monthly charges. This reconciles the risk estimate.
Deposit refund: September 7, subject to no damage or unpaid rent.
Notes: Committed team source: upstream/main 4ec519e88d9afe811a9d447f7aef8b3d81d473ce. roles/02_finance_analyst/finance.md and daily_projection.csv. Original inputs: inputs/cost_list.md, inputs/mall_facts.md and inputs/foot_traffic.csv. All figures are required-sales projections, not actual results. Risk source: roles/03_risk_manager/risks.md. The $7,875 opening estimate includes $225 of opening-day terminal, insurance and cleaning, whereas $7,650 pre-opening cash excludes those charges. Deposit is refundable and excluded from expenses.

## Slide 5
Break-even requires 1,926 sales by August 31
4
Chart: 
| 05-31 | 06-07 | 06-14 | 06-21 | 06-28 | 07-05 | 07-12 | 07-19 | 07-26 | 08-02 | 08-09 | 08-16 | 08-23 | 08-30 | 08-31
Revenue | 0 | 2952 | 5904 | 8838 | 11790 | 14742 | 17694 | 20646 | 23580 | 26226 | 28278 | 30348 | 32418 | 34470 | 34668
All project costs | 5150 | 6695.56 | 8216.12 | 10136.14 | 12256.7 | 16902.26 | 18822.82 | 20743.38 | 22863.4 | 27499.78 | 29193.34 | 30887.44 | 32781.54 | 34475.1 | 34657.04
2.96%
of passing visits must buy one item
$10.96
project surplus at the minimum sales target
About 21 items/day on average. The target includes August’s 30% traffic decline.
Notes: Committed team source: upstream/main 4ec519e88d9afe811a9d447f7aef8b3d81d473ce. roles/02_finance_analyst/finance.md and daily_projection.csv. Original inputs: inputs/cost_list.md, inputs/mall_facts.md and inputs/foot_traffic.csv. All figures are required-sales projections, not actual results. Cost basis charges all purchased inventory and equipment to the project, with no resale proceeds. At 1,926 sales revenue is $34,668.00 and cost is $34,657.04. Deposit is excluded from this chart.

## Slide 6
Operating risks and responses
5
Risk | Response | Owner
Cash runs short | Review sales and upcoming rent weekly. Keep one staffed position with agency relief. | Finance + Risk
August visits fall 30% | Prioritize June/July acquisition. Recheck forecast before the anchor closes July 31. | Marketing
Unpopular phone models tie up stock | Start with 300 items. Record requests and reorder proven sellers weekly. | Risk + Customer
Trading hours stay 10 AM–9 PM daily. Signs stay inside Unit 42 and need two business days for approval.
Notes: Committed team source: upstream/main 4ec519e88d9afe811a9d447f7aef8b3d81d473ce. roles/03_risk_manager/risks.md. Inputs: cost_list.md and mall_facts.md. Risk report identifies cost/cash pressure, August traffic decline and inventory cash tied up in unpopular models. One employee at a time requires shifts of no more than eight hours per person and agency relief.

## Slide 7
June customer plan: 685 sales
6
Chart: 
| Mon | Tue | Wed | Thu | Fri | Sat | Sun
Passing visits | 488 | 510 | 488 | 488 | 565 | 1529 | 1463
Audience and offer
Phone owners needing cases, cables or grips. Test students as an audience. Display the $18 price and phone compatibility clearly.
Timing and coverage
Focus promotion on weekend afternoons and weekday evenings. Staff every opening hour.
June target: $12,330 revenue from 23,122 passing visits.
Notes: Committed team source: upstream/main 4ec519e88d9afe811a9d447f7aef8b3d81d473ce. roles/01_customer_analyst/customers.md and roles/03_risk_manager/risks.md. inputs/foot_traffic.csv totals: Mon 488, Tue 510, Wed 488, Thu 488, Fri 565, Sat 1529, Sun 1463; total 5531. Weekends 54.1%. Peak weekend hour 14:00, weekday 18:00. Finance daily_projection.csv June 685 sales / 23122 visits = 2.96%, revenue $12330. Proposed promotion tactics and staff schedule are recommendations, not observed results.

## Slide 8
First-month marketing plan
1. Launch Campaign: Referral Discounts & Giveaways
Launch the pop-up with a promotional contest and a referral-based discount. Customers who make a purchase receive a 20% discount coupon to give to a friend or use on their next visit, encouraging word-of-mouth marketing, repeat purchases, and new customer acquisition.
2. High-Impact, Minimalist Outdoor Advertising
Place eye-catching, minimalist posters in strategic, high-traffic locations around town, such as major entry and exit routes, near high schools and universities, and in business districts. The goal is to create curiosity and build awareness before customers encounter the pop-up.
3. Viral Social Media Marketing
Create humorous, relatable, and highly shareable social media content designed to generate organic reach. Integrate the product or brand naturally into entertaining videos and posts, making the promotion feel like part of the content rather than a traditional advertisement.
Campaign proposal. Discounts, giveaways and poster costs require a revised financial forecast.
7
Notes: Campaign content supplied by Nicolas Delfau in chat. This replaces the original first-month launch schedule. The 20% coupon is a proposed discount, not a cost in the existing $18 full-price sales forecast. At a full 20% redemption, the selling price would be $14.40 and contribution after $4 stock and a 3% card fee would be $9.968, compared with $13.46 at full price. Coupon redemption rate, giveaway quantities, contest rules and poster printing/placement costs remain unspecified. The team should revise revenue and costs before adopting the campaign. Outdoor placements need permission from property owners and relevant authorities. Under inputs/mall_facts.md, signs on mall premises stay inside the leased footprint and mall approval takes two business days. Social reach is an objective, not a guaranteed result. Other slides and financial figures are preserved from the existing deck.